## Daily Tracker
Frontend Developer #1 — Universal Admin Dashboard Theme
40 Working Days · 8 Hours/Day · Fill in Date, Status, Hours, and Notes every day.
Day | Date | Week | Task / Focus for the Day | Status | Hours Worked | GitHub Commit | Notes / Blocked Reason
1 | 23rd August | Week 1 | Project guide review + Week 1 planning | Done | 8 hrs | cade797 | Read project guide, understood reusable admin dashboard goal, reviewed required folder structure and workflow.
2 | 24th August |  | Setup + understand the starter project | Done | 8 hrs | cade797 | Setup completed, project running, starter structure reviewed, GitHub repo and branches configured.
3 | 25th August |  | TypeScript basics + component props practice | Done | 8 hrs | cade797 | Reviewed interfaces, typed props, reusable component rules, and project component responsibilities.
4 | 26th August |  | Sitemap for admin dashboard pages | Done | 8 hrs | cade797 | Mapped required pages: auth, dashboard, users, roles, categories, content, media, notifications, reports, analytics, settings, and profile.
5 | 27th August |  | Wireframe approval + setup verification | Done | 8 hrs | cade797 | Confirmed dashboard flow, verified lint/build, and prepared project for Week 2 homepage section work.
6 | 28th August | Week 2 | Build responsive homepage structure and shared layout | Done | 8 hrs | Pending commit | Created the homepage structure with reusable layout components, theme configuration, responsive navigation, and consistent page spacing.
7 | 29th August |  | Build page header and KPI card section | Done | 8 hrs | Pending commit | Added the dashboard page header and reusable KPI cards with values, change indicators, trends, and responsive grid behavior.
8 | 30th August |  | Create weekly analytics chart section | Done | 8 hrs | Pending commit | Built the weekly analytics visualization from typed mock data and added responsive chart labels, bars, and supporting context.
9 | 31st August |  | Add recent activity and recent records sections | Done | 8 hrs | Pending commit | Implemented recent activity and recent records sections with typed data, status labels, responsive tables, and reusable card containers.
10 | 1st September |  | Add quick actions and verify the homepage | Done | 8 hrs | Pending commit | Completed quick actions, checked the homepage section order, tested responsive behavior, and verified the production build.
11 | 2nd September | Week 3 | Build login page | Done | 8 hrs | Pending commit | Created the login screen with typed form fields, password recovery navigation, remember-me control, and reusable authentication styling.
12 | 3rd September |  | Build registration and forgot-password pages | Done | 8 hrs | Pending commit | Added registration and password-reset routes with shared authentication components, validation-ready fields, and success states.
13 | 4th September |  | Create dashboard inner page and admin layout | Done | 8 hrs | Pending commit | Built the dashboard route and shared admin shell with header, sidebar, notifications access, profile access, and responsive content area.
14 | 5th September |  | Create users management page | Done | 8 hrs | Pending commit | Implemented the users module with summary metrics, searchable records, status indicators, reusable dialogs, and typed mock data.
15 | 6th September |  | Connect routing and verify the first inner pages | Done | 8 hrs | Pending commit | Connected the authentication, dashboard, and users routes, confirmed navigation behavior, and ran TypeScript and production build checks.
16 | 7th September | Week 4 | Build roles and categories pages | Done | 8 hrs | Pending commit | Created reusable roles and categories management pages with module-specific records, status values, summaries, and create/detail flows.
17 | 8th September |  | Build content and media pages | Done | 8 hrs | Pending commit | Added content and media management pages with typed data, responsive tables, filtering, record details, and module actions.
18 | 9th September |  | Build notifications, reports, and analytics pages | Done | 8 hrs | Pending commit | Implemented notifications and reports modules plus an analytics page with metrics, traffic charts, and channel breakdowns.
19 | 10th September |  | Build settings and profile pages | Done | 8 hrs | Pending commit | Created settings and profile forms with reusable cards, account information, workspace preferences, and notification controls.
20 | 11th September |  | Finish DataTable, Sidebar, and Modal components | Done | 8 hrs | Pending commit | Completed the required reusable components: searchable and sortable DataTable with pagination, responsive collapsible Sidebar, and accessible Modal.
21 | 12th September | Week 5 | Create reusable module data and page pattern | Done | 8 hrs | Pending commit | Centralized typed module definitions and created a shared management-page pattern for users, roles, categories, content, media, notifications, and reports.
22 | 13th September |  | Improve the responsive admin shell | Done | 8 hrs | Pending commit | Added mobile navigation, route-aware sidebar states, shared search, notification indicator, profile summary, and responsive content sizing.
23 | 14th September |  | Add module summaries and status presentation | Done | 8 hrs | Pending commit | Added live summary cards, consistent status badges, typed column definitions, search, sorting, pagination, loading, and empty states.
24 | 15th September |  | Complete dashboard and analytics modules | Done | 8 hrs | Pending commit | Expanded the dashboard with KPI metrics, charts, activity, recent records, and quick actions, then completed the analytics module.
25 | 16th September |  | Complete forms and Week 5 verification | Done | 8 hrs | Pending commit | Finished module dialogs, settings and profile interactions, checked all required routes, and verified a successful production build.
26 | 17th September | Week 6 | Add React Hook Form and Zod validation | Done | 8 hrs | Pending commit | Integrated React Hook Form with Zod schemas for login, registration, password reset, module creation, settings, and profile forms.
27 | 18th September |  | Add persisted Zustand state management | Done | 8 hrs | Pending commit | Created a typed Zustand store with local persistence for module records, workspace settings, profile data, and shared admin state.
28 | 19th September |  | Add create, delete, confirmation, and toast flows | Done | 8 hrs | Pending commit | Implemented validated record creation, detail dialogs, delete confirmation, live table updates, and timed dismissible success messages.
29 | 20th September |  | Persist settings and profile data | Done | 8 hrs | Pending commit | Connected settings and profile forms to shared persisted state, added submitting states, header profile updates, and demo-data reset controls.
30 | 21st September |  | Polish UI and complete Week 6 testing | Done | 8 hrs | Pending commit | Applied the universal dark-indigo dashboard theme, refined spacing and typography, cleared the development cache issue, and passed build and route checks.
31 |  | Week 7 | Wire up config for dynamic content + responsive QA | Todo
32 |  |  |  | Todo
33 |  |  |  | Todo
34 |  |  |  | Todo
35 |  |  |  | Todo
36 |  | Week 8 | Bug fixing, content polish, deployment, final presentation | Todo
37 |  |  |  | Todo
38 |  |  |  | Todo
39 |  |  |  | Todo
40 |  |  |  | Todo
40 |  |  |  | Todo